## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 05/May/2022 | Rev.:03
|  | Comment Sheet Ref.No.: | Doc Description: P&ID FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00130 | Doc. No.: BU-20-VD-303-PR-DWG-0013
|  | Transmittal Date: 10/Mar/2022 | Doc Rev.: 03
Item | CHCE Comment |  |  | Vendor Clarification
1 | Suction/Discharge pressure and temperature and design condition of each stage must be reported separately. |  |  | noted and updated CES reply: Closed.
2 | OP and DP shall be rechecked and revised. |  |  | noted and updated CES reply: Closed.
3 | Considering the fact that the discharge pressure is 23.5, STOP set point must be double-checked. |  |  | noted and updated CES reply: Closed.
4 | All PSVs inlet/outlet size rating and orifice designation as per API letter shall be specified. |  |  | Noted and updated, however calculation is awaited CES reply: Closed.
5 | To be deleted |  |  | noted and updated CES reply: Closed.
6 | Valve type schematic shall be modified (globe) |  |  | noted and updated CES reply: Closed.
7 | Please specify process connection size |  |  | noted and updated CES reply: Closed.
8 | Since compressor discharge pressure is 23.5, The set points shall be checked again. |  |  | noted and updated CES reply: Please refer to latest comment on P&ID.
9 | BU-20-D-100-PR-PID-101 11/2"-NM-1021-539D(H) |  |  | noted and updated CES reply: Closed.
10 | BU-20-D-100-PR-PID-101 2"-CWS-1013-500C(N) |  |  | noted and updated CES reply: Closed.
11 | PG-10161 |  |  | noted and updated CES reply: Closed.
12 | Please be advised that as per above picture cooling water line 2" can be prepared by client in vendor battery limit .AIRPACK is expected to check the cooling water line again and select suitable line size. |  |  | we have checked the calculation and we have updated it to 2" to be on the safe side CES reply: Closed.
13 | BU-20-D-100-PR-PID-101 2"-NL-1002-511C(N) |  |  | noted and updated CES reply: Closed.
14 | Considering the fact that the discharge pressure is 23.5, STOP set point must be double-checked. |  |  | noted and updated CES reply: Closed.
15 | XCS-108 |  |  | noted and updated CES reply: Closed.
16
17 | - FO data sheet must be added to instrument data sheet. - PSV and on-off valve data sheet must be revised. - As per control valve data sheet one "pressure control valve" with no tag was mentioned in data sheet that was not specified in P&ID, please specify mentioned valve and consider tag no for it. |  |  | - Noted will be added to instrument data sheets, no need to comment on P&ID - Noted will be added to instrument data sheets, no need to comment on P&ID - Noted will be updated no need to comment on P&ID CES reply: Closed.
18 | Shall be checked again based on PSV set pressure. |  |  | Noted and updated CES reply: Closed.
19 | With reference to clause 7.6.5 of API 618 5th edition, PSV set pressure shall be at least 10% above discharge pressure. Therefor, PSV set pressure shall be at least 24.8 barg. |  |  | Noted and updated CES reply: Closed.
20 | Discrepancy with "trip & alarm set point list" |  |  | Please comment on alarm and trip set point list CES reply: Closed. Will be stated in mentioned document as well.
21 | These shall be checked again based on PSV set pressure. |  |  | Noted and updated CES reply: Closed.
22 | PSV set pressure shall be checked considering clause 7.6.5 of API 618 5th edition. |  |  | Noted and updated CES reply: Closed.
23 | As per project mechanical data sheet, nitrogen discharge temperature at the battery limit of package shall be less than 52 C. So, in order to eliminate any discrepancy with project document and also since the value 40 C is in the limitation of alowable temperature, please change 40 C to Max 52 C. |  |  | Noted and updated CES reply: Closed.
24 | Approve For Construction |  |  | Noted and updated CES reply: Closed.
25 | Modify the MC logo |  |  | Noted and updated CES reply: Closed.
26 | 1. PID must be revised based on the comment on CONTROL PHILOSOPHY FOR NITROGEN GAS BOOSTER. the comment is pasted here: "Please be noted that there is a buffer tank downstream 20-C-7080 and ultimate goal is to keep the pressure of buffer tank at a constant value. It is worth mentioning that in normal operation the buffer tank has no discharge. This concept is also mentioned in the relevant data sheet. In 20-C-1002 the compressor is in service continuously, there is no need to start/stop automatically". 2. Please clarify why some pressure values are in "barg" and some in "bara". A unique pattern must be followed |  |  | 1. I have deleted automatic start and stop from the load / unload set points, this should be sufficient. CES reply: Closed. 2. updated accordingly, only water circuit is barg now. CES reply: Closed.
27 | ? |  |  | Noted and updated CES reply: Closed.
28 | 6. 4"X2" |  |  | Noted and updated CES reply: Closed.
29
30 | 1. 52 oC |  |  | Noted and updated
31 | Set point for PAH-10156 has discrepancy with document Trip and Alarm Set point List that must be modified. |  |  | Noted will be updated in next revision
32 | There is discrepancy with compressor data sheet. With reference to mechanical data sheet of instrument air compressor, discharge pressure of first stage is reported 14.5 barg. |  |  | Noted and updated
33 | 3. Discharge of first stage is reported 14.5 bara |  |  | 13,5 bar(a) as per latest revision of datasheet
34 | Design temperature shall be at least 85 C. |  |  | Noted and updated
35 | 3. Discharge of first stage is reported 14.5 bara |  |  | 13,5 bar(a) as per latest revision of datasheet
36 | Shall not be less than 85 C. |  |  | Noted and updated
37 | Shall be checked with pulsation dampener data sheet. |  |  | Noted and updated
38 | Please check it again considering PSV set pressure. Also as per mechanical data sheet of after cooler, design pressure is 26 bara. |  |  | Noted and updated
39 | Shall not be less than 85 C. |  |  | Noted and updated
40 | TAHH (10154) set temperature is 140 C. How is it possible pulsation dampener design temperature be less than TAHH? |  |  | Noted and updated
41 | Shall be checked with pulsation dampener data sheet. |  |  | Noted and updated
42 | 2. 23.5 bara |  |  | Noted and updated
43
44