## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 06/May/2022 | Rev.:04
|  | Comment Sheet Ref.No.: | Doc Description: PULSATION DAMPER MECHANICAL DATA SHEET FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00131 | Doc. No.: BU-20-VD-303-ME-DSH-0027
|  | Transmittal Date: 06/May/2022 | Doc Rev.: 04
Item | CHCE Comment |  |  | Vendor Clarification
1 | Mechanical items will be checked after sending pulsation dampener calculation. |  |  | Noted, however please confirm datasheet is ok, calculation will be submitted soon CES reply: Closed.
2 | Following items shall be added to data sheet: 1- Dampener thickness. 2- RAL number of pulsation dampener. 3- Maximum Allowable Compressor Cylinder Flange Pressure Pulsation as per clause 7.9.4.2.5.2.1 of API618. 4- Maximum Allowable Pulsation Limits at and Beyond Line-side Nozzles of Pulsation Suppression Devices as per clause 7.9.4.2.5.2.2.1 of API 618. 5- Pulsation dampener design approach shall be added to document. 6- Maximum Allowable Pressure Drop as per clause 7.9.4.2.5.3.1 of API 618. 7- Capacity of pulsation dampener will be checked after specifying cylinder stroke and cylinder diameter. 8- DESIGN APPROACH STUDY SHALL BE ADDED. |  |  | 1.Noted and added CES reply: Closed. 2. Noted and added CES reply: Closed. 3. Noted and added CES reply: Closed. 4. Noted and added CES reply: Closed. 5. Noted and added CES reply: Closed. 6. Noted and added CES reply: Closed. 7. Noted CES reply: Closed. 8. Noted and added CES reply: Closed.
3 | Shall be specified in next revision. |  |  | updated CES reply: Closed.
4 | Exact material grade shall be added. |  |  | updated CES reply: Closed.
5 | 3 mm. |  |  | updated CES reply: Closed.
6 | Discrepancy with PID. |  |  | updated CES reply: Closed.
7 | Discrepancy with PID. On PID DP is reported 21 bara. |  |  | updated CES reply: Closed.
8 | Discrepancy with PID. On PID DP is reported 35.25 bara. |  |  | updated CES reply: Closed.
9 | Exact material grade shall be added. |  |  | updated CES reply: Closed.
10 | 1300#???? |  |  | updated CES reply: Closed.
11 | 3 mm. |  |  | updated CES reply: Closed.
12 | 1- Based on these data compressor data sheet shall be updated. 2- Percentage of allowable peak-peak pulse @ cylinder flange shall be added to document. |  |  | 1. Noted and will be updated 2. This was updated CES REPLY: Closed.
13 | With reference to clause 4.5 of BU-20-D-000-PR-SPC-101 (ESS FOR AMBIENT, SITE CONDITION & UTILITY DATA), design temperature shall be at least 85C. |  |  | updated
14 | Test pressure shall be specified here clearly as a number. Also MAWP is not specified in this data sheet |  |  | This will be specified in calculation documents of pulsation dampers CES REPLY: Closed.
15 | RAL color shall be deleted. Painting shall be as per APPROVED painting procedure. |  |  | updated CES REPLY: Closed.
16 | Please check it again. |  |  | updated CES REPLY: Closed.
17 | Please check the pressure with compressor data sheet. Discharge pressure of stage 1 is 14.5 barg. |  |  | updated CES REPLY: Closed.
18 | Please check the capacity again. With reference to compressor data sheet, suction pressure is 7,8,9 bara and discharge of stage 1 is 15.5 bara. Therefor, capacity of pulsation dampener considering suction pressure 9 bara and discharge pressure 15.5 bara is almost 100 liter. Vd= 1.6x (Vs/r1/k) |  |  | based on simulation 80 Liters is sufficient CES reply: With reference to clause 7.9.3.2 of API 618 5th and CES comments in revision 01, Vd= 1.6x (Vs/r1/k). Therefor, discharge pulsation dampener capacity of first stage of compressor shall not be less than 98 Lit. Also please be noted that volume of pulsation dampener can be calculated as per formula of design approach 1 even if pulsation dampener is designed as per design approach 2. If 96 liter inlet pulsation dampener will apply (based on pulsation dampener drawing) , discharge pulsation dampener capacity shall not be less than 105 liter. Airpack Reply: We are using desing approach 2 (as per 6th edition, approach one is no longer applicable and cannot be used) therefore the current calculation of the sizes of the pulsantion dampers is correct and will not be changed
19 | With reference to latest comments on P&ID, PSV set pressure shall be at least 10% above operating pressure. Therefore, disign pressure shall be revised. |  |  | updated CES REPLY: Please see latest comment.
19 | As per mechanical data sheet of compressor, design temperature is 210 C. |  |  | Mechanical datasheet will be updated CES reply: Closed.
19
19 | 6. Discrepancy with PID. PID shall be revised. |  |  | P&ID will be revised
19 | Please check the design pressure with pulsation dampener drawing. |  |  | Noted and updated
19 | 1. 5-52 oC |  |  | Noted and updated
19 | With reference to pulsation dampener drawing, design temperature is 210 C. |  |  | drawing will be updated to 0-85
19 | With reference to pulsation dampener drawing, capacity is 96 lit. |  |  | Noted and updated
19 | 7. Discrepancy with PID. design pressure shall not be less than PSV set pressure. |  |  | Noted and updated
19 | With reference to P&ID, design pressure is 26 bara. |  |  | Noted and updated
19 | With reference to clause 7.9.3.2 of API 618 5th and CES comments in revision 01, Vd= 1.6x (Vs/r1/k). Therefor, discharge pulsation dampener capacity of first stage of compressor shall not be less than 98 Lit. Also please be noted that volume of pulsation dampener can be calculated as per formula of design approach 1 even if pulsation dampener is designed as per design approach 2. If 96 liter inlet pulsation dampener will apply, discharge pulsation dampener capacity shall not be less than 105 liter. |  |  | Airpack Reply: We are using desing approach 2 (as per 6th edition, approach one is no longer applicable and cannot be used) therefore the current calculation of the sizes of the pulsantion dampers is correct and will not be changed
19 | 3. As per P&ID, design pressure is 26 bara. |  |  | P&ID will be revised
19 | 4. Please revise P&ID. |  |  | P&ID will be revised
19 | With reference to pulsation dampener drawing, capacity is 38 liter. |  |  | Noted and updated
19 | with reference to compressor data sheet discharge temperature of stage 2 is reported 134 C. |  |  | 2nd stage is 83 as per datasheet, it has been updated other document will be updated as well
19 | 5. P&ID shall be revised considering 85 C. |  |  | Noted and updated
19 | With reference to pulsation dampener drawing, capacity is 48 liter. |  |  | Noted and updated
19
19 | Repetitive comment :With reference to mechanical data sheet of nitrogen compressor and P&ID of nitrogen compressor, design temperature is 210 C. |  |  | design temperature of pulsation damper is 170°C, based on actual outlet temperature of 134°C
19 | Please check it again. with reference to P&ID of nitrogen compressor TAHH (10155) is 140 C. Therefor, design temperature shall not be less than 140 C. |  |  | This temperature has been updated in P&ID
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19