## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 09/May/2022 | Rev.:01
|  | Comment Sheet Ref.No.: | Doc Description: Calculation & Datasheet of Safety valves for Nitrogen Gas Booster
|  | Transmittal No.: APCES-V-00132 | Doc. No.: BU-20-VD-303-IN-DSH-0015
|  | Transmittal Date: 09/05/2022 | Doc Rev.: 01
Item | CHCE Comment |  |  | Vendor Clarification
1 | Required capacity for each PSV shall be specified by Airpack. |  |  | Updated in next revision
2 | PSVs pre-calculation shall be submitted by Airpack. |  |  | Not applicable
3 | Sub-vendor's calculation must be attached. |  |  | Updated in next revision
4 | VTA items to be specified in next rev. |  |  | Updated in next revision
5 | This document must be consistent with the revised PID. |  |  | Updated in next revision
6 | Approve for construction |  |  | Updated in next revision
7 | 100°C must be considered for all cooling water lines |  |  | Updated in next revision
8 | 7 barg must be considered for all cooling water lines |  |  | Updated in next revision
9 | 52 |  |  | Updated in next revision
10
11
12
13
14
15
16
17
18
19
20
21