## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 09/May/2022 | Rev.: 01
|  | Comment Sheet Ref.No.: | Doc Description: After cooler mechanical strenght calculation
|  | Transmittal No.: APCES-V-00132 | Doc. No.: BU-20-VD-303-ME-CAL-0016
|  | Transmittal Date: 09/May/2022 | Doc Rev.: 01
Item | CHCE Comment |  |  | Vendor Clarification
1 | With reference to clause M8 of TCL PV ELITE native file shall be submitted. |  |  | It was never agreed to submit a Native file for the strength calculation, during KOM it was decided to only suply PDF file, please check the minutes. CES reply (May.09,2022): It was agreed. Order of nitrogen compressor has been placed after K.O.M. Therefore, Native file shall be submitted. See clause M8 of TCL of nitrogen compressor. Airpack reply: KOM was common for both compressors, therefore it should be considered for both.
2 | as per requesition, it mentiones that it has to be considered for the package, not for separate items this will not be done. |  |  | as per requesition, it mentiones that it has to be considered for the package, not for separate items this will not be done.