## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 13/May/2022 | Rev.:02
|  | Comment Sheet Ref.No.: | Doc Description: PULSATION DAMPER DETAIL DRAWING FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00134 | Doc. No.: BU-20-VD-303-ME-DWG-0079
|  | Transmittal Date: 13/May/2022 | Doc Rev.: 02
Item | CHCE Comment |  |  | Vendor Clarification
1 | Pulsation dampener calculation with PV ELITE native file shall be sent before next revision of pulsation dampener drawing. |  |  | PV-elite calculation has been submitted as PDF as per MOM of KOM CES reply (May.10,2022): Will be descussed in related document.
2 | 26 barg |  |  | is already mentioned CES reply (May.10,2022): See the latest comment in document.
2 | Shall be checked with P&ID. |  |  | P&ID has been updated CES reply (May.10,2022): Closed.
2 | Since TAHH (10155) is 140 C, design temperature shall not be less than 140 C. |  |  | P&ID has been updated CES reply (May.10,2022): Considering 2 C margin between operating temperature and design temperature is not enough and logical. Please consider at least 15 C margin between them.
2 | As per compressor data sheet discharge temperature is 81 C. |  |  | there is a typo in the datasheet CES reply (May.10,2022): Closed. We are waiting to receive revised data sheet.
2 | With reference to mechanical data sheet of pulsation dampener design pressure is 14.5 barg. |  |  | is already mentioned CES reply (May.10,2022): Closed.
2 | With reference to P&ID design temperature is 210 C |  |  | on the P&ID 170°C is mentioned CES reply (May.10,2022): Closed.
2 | 26 barg |  |  | is already mentioned CES reply (May.10,2022): See the latest comment in document.
2 | 26 barg |  |  | is already mentioned CES reply (May.10,2022): See the latest comment in document.
2
2 |  |  |  | all comments are updated in this revision
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2