## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 13/May/2022 | Rev.:02
|  | Comment Sheet Ref.No.: | Doc Description: PULSATION DAMPER DETAIL DRAWING FOR EMERGENCY INSTRUMENT AIR COMPRESSOR
|  | Transmittal No.: APCES-V-00134 | Doc. No.: BU-20-VD-303-ME-DWG-0080
|  | Transmittal Date: 13/May/2022 | Doc Rev.: 02
Item | CHCE Comment |  |  | Vendor Clarification
1 | Pulsation dampener calculation with PV ELITE native file shall be sent before next revision of pulsation dampener drawing. |  |  | PV-elite calculation has been submitted as PDF as per MOM of KOM CES reply (May.10,2022): Closed.
2 | 14.5 barg. |  |  | Noted is already mentioned CES reply (May.10,2022): See the latest comments.
2 | 26 barg |  |  | Noted is already mentioned CES reply (May.10,2022): See the latest comments.
2
2 |  |  |  | all comments are updated in this revision
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2