## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 16/Jun/2022 | Rev.: 02
|  | Comment Sheet Ref.No.: | Doc Description: After cooler mechanical strenght calculation
|  | Transmittal No.: APCES-V-00150 | Doc. No.: BU-20-VD-303-ME-CAL-0016
|  | Transmittal Date: 16/Jun/2022 | Doc Rev.: 02
Item | CHCE Comment |  |  | Vendor Clarification
1 | With reference to clause M8 of TCL PV ELITE native file shall be submitted. |  |  | It was never agreed to submit a Native file for the strength calculation, during KOM it was decided to only suply PDF file, please check the minutes. CES reply (May.09,2022): It was agreed. Order of nitrogen compressor has been placed after K.O.M. Therefore, Native file shall be submitted. See clause M8 of TCL of nitrogen compressor. Airpack reply: KOM was common for both compressors, therefore it should be considered for both. CES reply (May.12,2022): As per TCL of nitrogen compressor PV ELITE native file shall be submitted. Also, order of nitrogen compressor has been placed after K.O.M.
2 | as per requesition, it mentiones that it has to be considered for the package, not for separate items this will not be done. |  |  | as per requesition, it mentiones that it has to be considered for the package, not for separate items this will not be done.
3 | Repetitive comment: 1- Wind and seismic (as per ASCE 7-16 (see report in page 13 of requisition)) effect for design all pressure vessels (even if located inside of package) shall be considered by vendor. |  |  | As discussed during the meeting on 14th of June, we have submitted a warrantee letter for the wind and seismic loads. based on this please approve these drawings.