## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 16/Jun/2022 | Rev.:04
|  | Comment Sheet Ref.No.: | Doc Description: PULSATION DAMPER DETAIL DRAWING FOR EMERGENCY INSTRUMENT AIR COMPRESSOR
|  | Transmittal No.: APCES-V-00150 | Doc. No.: BU-20-VD-303-ME-DWG-0080
|  | Transmittal Date: 16/Jun/2022 | Doc Rev.: 04
Item | CHCE Comment |  |  | Vendor Clarification
1 | Pulsation dampener calculation with PV ELITE native file shall be sent before next revision of pulsation dampener drawing. |  |  | PV-elite calculation has been submitted as PDF as per MOM of KOM CES reply (May.10,2022): Closed.
2 | 14.5 barg. |  |  | Noted is already mentioned CES reply (May.10,2022): See the latest comments.
2 | 26 barg |  |  | Noted is already mentioned CES reply (May.10,2022): See the latest comments.
2
2 |  |  |  | all comments are updated in this revision CES reply (May.15,2022): It is not implemented yet. Wind and seismic effect in design of pulsation dampener shall be considered by vendor.
2
2 | Repetitive comment: wind and seismic effect for design of equipment shall be considered by vendor. |  |  | as mentioned and explained in previous E-mail this is not required for these small vessels. CES reply (Jun.08,2022): Regardless of size of pulsation dampeners and heat exchangers wind and seismic effect shall be considered in design of all equipment. It is clearly stated in material requisition, ASCE 7-16 shall be considered in design of all equipment and packages. As discussed during the meeting on 14th of June, we have submitted a warrantee letter for the wind and seismic loads. based on this please approve these drawings.
2
2 | ~ |  |  | updated
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2