## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 03/Aug/2020 | Rev.: 04
|  | Comment Sheet Ref.No.: | Doc Description: Surface preparation & painting procedure
|  | Transmittal No.: APCES-V-00171 | Doc. No.: BU-20-VD-303-PI-DCR-0010
|  | Transmittal Date: 03/Aug/2022 | Doc Rev.: 04
Item | CHCE Comment |  |  | Vendor Clarification
1 | 1- as per TCL final RAL number shall be as per project panting specification. 2- Based on vendor criteria equipment with temperature above 150 C need special RAL number. PSV, compressor and pulsation dampener are working in same temperature but RAL number is different. Please clarify. |  |  | This is special paint fur high temperatures which does not come in any specific RAL color, just Aluminium finish, so we cannot change the RAL color. PSV has been updated CES reply (Jul.17,2022): Since there is the deviation from project painting RAL. No. , TQ shall be submitted. Vendor is expected to explain technically the reason of his deviation from project specification. Also, painting data sheet attached to your TQ (without painting data sheet your TQ will not accepted. Airpack Reply: we do not want to go into the TQ, this will take time and next week we will start the painting. if you do not want further delay in this project please accept the document as is. this is not a serious issue. and we have mentioned this from the first revision of the project. I have attached the datasheet to the CRS for your informaiton. please approve the painting procedure in this revision. TQ is approved
2 | project Ral No. shall be met please add paint data sheet |  |  | This is special paint fur high temperatures which does not come in any specific RAL color, just Aluminium finish, so we cannot change the RAL color. CES reply (Jul.17,2022): Since there is the deviation from project painting RAL. No. , TQ shall be submitted. Vendor is expected to explain technically the reason of his deviation from project specification. Also, painting data sheet attached to your TQ (without painting data sheet your TQ will not accepted. Since there is the deviation from project painting RAL. No. , TQ shall be submitted. Vendor is expected to explain technically the reason of his deviation from project specification. Also, painting data sheet attached to your TQ (without painting data sheet your TQ will not accepted. Airpack Reply: we do not want to go into the TQ, this will take time and next week we will start the painting. if you do not want further delay in this project please accept the document as is. this is not a serious issue. and we have mentioned this from the first revision of the project. I have attached the datasheet to the CRS for your informaiton. please approve the painting procedure in this revision.TQ is approved