## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 17/Aug/2022 | Rev.:01
|  | Comment Sheet Ref.No.: | Doc Description: RECIPOCRATING COMPRESSOR DETAIL DRAIWNG WITH PARTS LIST FOR EMERGENCY INSTRUMENT AIR COMPRESSOR
|  | Transmittal No.: APCES-V-00176 | Doc. No.: BU 20 VD 303 ME DWG 0077
|  | Transmittal Date: 17/Aug/2022 | Doc Rev.: 01
Item | CHCE Comment |  |  | Vendor Clarification |  |  | CES Reply | Vendor Clarification
1 | 1-Unloader valve detail drawing shall be added. 2- Material of all parts shall be added to document 3- Rod packing shall be shown |  |  | 1. added. CHCE reply (Jul.27,2022): Closed. Airpack reply: Noted 2. will not be shown CHCE reply (Jul.27,2022): Shall be shown same as SIAD company in MEG plant. See attached picture. Airpack reply: We will not show all the materials, any material required to show is already shown in the compressor datasheet. SIAD compressor is much bigger, so more detailes information can be given. 3. already part of this document CHCE reply (Jul.27,2022): Please specify manufacturer part NO. Airpack reply :Drawing CC0819 Gland gas
2 | 1. Oil spacer assembly shall be shown. 2. See reply sheet. |  |  | 1. please clarify what is meant with oil spacer assembly 2. see above reply.
3
4
5