## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 13/Sep/2022 | Rev.:03
|  | Comment Sheet Ref.No.: | Doc Description: RECIPOCRATING COMPRESSOR DETAIL DRAIWNG WITH PARTS LIST FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00180 | Doc. No.: BU 20 VD 303 ME DWG 0024
|  | Transmittal Date: 13/Sep/2022 | Doc Rev.: 03
Item | CHCE Comment |  |  | Vendor Clarification |  |  | CES Reply | Airpack reply
1 | 1-Unloader valve detail drawing shall be added. 2- Material of all parts shall be added to document 3- Rod packing shall be shown |  |  | 1. added. CHCE reply (Jul.27,2022): Closed. Airpack reply: Noted 2. will not be shown CHCE reply (Jul.27,2022): Shall be shown same as SIAD company in MEG plant. See attached picture. Airpack reply: We will not show all the materials, any material required to show is already shown in the compressor datasheet. SIAD compressor is much bigger, so more detailes information can be given. CHCE reply (Aug.17,2022): Regardless of size of compressor, material of all parts shall be written in document. Material is required for spare part and will be used by the operator during maintenance of compressor. 3. already part of this document CHCE reply (Jul.27,2022): Please specify manufacturer part NO. Airpack reply :Drawing CC0819 Gland gas CHCE reply (Aug.17,2022): Closed. |  |  | 1. Closed 2. we are not showing all materials, this is not part of this documents. Also if you want to buy spare parts, you don’t need the material, you have to by from Airpack with our item/tag number. CHCE reply (Sep.07,2022): This document will be approved after specifying material of all parts. 3. No, Only Airpack numbers are supplied. 4. Closed | 2. as mentioned before nowhere it is mentioned that material for each part should be specified, there is no reason to not approve this document. If this doucment is not approved in next revision, the project will be put on hold until the document is approved.
2 | 1. Oil spacer assembly shall be shown. 2. See reply sheet. |  |  | 1. please clarify what is meant with oil spacer assembly CHCE reply (Aug.17,2022): See attached picture, oil wiper system or oil spacer system. If it is already shown please specify manufacturer part number. 2. see above reply. |  |  | 1. ok, oil gland /wiper is Drawing CC0806 CHCE reply (Sep.07,2022): Closed. 2. see above reply. CHCE reply (Sep.07,2022): Closed.
3
4
5