## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 18/Nov/2022 | Rev.:03
|  | Comment Sheet Ref.No.: | Doc Description: Sub Vendor list
|  | Transmittal No.: APCES-V-00196 | Doc. No.: BU-20-VD-303-PE-LST-0002
|  | Transmittal Date: 18/Nov/2022 | Doc Rev.: 03
Item | CHCE Comment |  |  | Vendor Clarification
1 | UCP Local MCC Local Control Panel (LCP) Electrical heater |  |  | Repeated answer - UCP >>> added electrical panel EX CES REPLY (Sep.10,2022): UCS is different from electrical panel. UCPs manufacturer shall be added to sub-vendor list. - Local MCC >>> added electrical panel Safe Area CES REPLY (Sep.10,2022): Local MCC (power distribution panel) is located in ZONE2 IIC T3. Manufacturere of power distribution panel shall be specified in sub-vendor list. Added - Local Control Panel (LCP) >> added electrical panel EX CES REPLY (Sep.10,2022): Since local panel is somthing different from local MCC (power distribution panel), separat row shall be inserted to document. Same discipline is making the cabinet, Same manufacture wil be used. - Electrical heater >>> part compressor; manufacturing standard CES REPLY (Sep.10,2022): Manu standard is related to standard design. If compressor manufacturer is manufacturer of oil heater, it shall be specified in sub-vendor list. Added