## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 09/Jan/2023 | Rev.:00
|  | Comment Sheet Ref.No.: | Doc Description: HAZOP / SIL REPORT
|  | Transmittal No.: APCES-V-00208 | Doc. No.: BU-20-VD-303-QC-REP-0105
|  | Transmittal Date: 09/Jan/2023 | Doc Rev.: 00
Item | CHCE Comment |  |  | Vendor Clarification |  |  | CES Reply | Vendor Clarification
1 | SIL REPORT |  |  | This report is a combined HAZOP / SIL report and therefor the titel will remain unchanged
2 | CES SF Comment: SIL verification report shall be provided by AIR PACK. |  |  | see comment 8
3 | Table 3 is Node list! |  |  | Noted and updated
4 | Target SIL |  |  | Noted and updated
5 | CES SF Comment: SIFs list table shall be completed and following items shall be added: SIF No. SIF description Voting ESD/Interlock No. Target SIL All SIFs even not SIL rated. |  |  | This is a summary of the SIL allocation, full list can be found in the attachment : HAZOP and SIL worksheet.
6 | CES SF Comment: close out report shall be provided by AIR PACK and to be approved by HAZOP leader. |  |  | see comment 8
7 | CES SF Comment; SIL 0 is not defined, please use IEC classification. |  |  | SIL 0 means no SIL, no update required. Our approved procedure is followed)
8 | CES SF Comment: action close out report shall be provided by AIR PACK for these recommendations and relevant vendor documents shall be revised accordingly. |  |  | Please provide you close-out details for point 02.1.1.2.1 and 04.1.1.2.1. after we have received this we will provided the close-out report seperately.
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56