## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 14/Jul/2023 | Rev.:02
|  | Comment Sheet Ref.No.: | Doc Description: Two years spare parts list
|  | Transmittal No.: APCES-V-00218 | Doc. No.: BU-20-VD-303-ME-LST-0054
|  | Transmittal Date: 14/Jul/2023 | Doc Rev.: 02
Item | CHCE Comment |  |  | Vendor Clarification |  |  | CES Reply | Vendor Clarification
1 | All items mentioned in attached file shall be supplied by AIRPACK for commissioning spare part list. |  |  | noted and completed
2 | Model number of VT, PT, TT, and FT shall be specified. |  |  | noted and completed
3 | DE or NDE shall be specified. Also, code of bearing as per motor data sheet shall be written. |  |  | noted and completed
4 | Pulsation dampeners. |  |  | noted and completed
5 | Relay, barrier and etc. shall be written in individual row. |  |  | noted and completed
614:23B1614:2214:24B1614:2214:261414:51 | Exact quantity shall be written not the percent. |  |  | noted and completed
7 | - Size of all o-ring and gasket shall be specified. - Some items are missing. For example fan of electrical motor, tube of heat exchanger and etc. See general comment in page 1.I16 |  |  | will not be included according to TQ that was received on 20-02-2023
8 | Exact material shall be specified. |  |  | will not be included according to TQ that was received on 20-02-2023
9 | Project document for example instrument data sheet or etc. shall be written in reference document column. |  |  | noted and completed
10 | Piston ring and guide ring shall be written in individual row. |  |  | noted and completed
11 | - Spar part of each compressor shall be specified in individual page. - Electrical motor, instrumentation, mechanical items, PLC and etc. shall be specified in individual columns of each compressor page. Please see the sample SPLIR form. |  |  | noted and completed
12 | Manner of filling SPLIR format shall be same as attached file. |  |  | see above
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56