## Resolution Sheet
|  |  |  | PROJECT: | ABT 360 KT/Y PP PLANT Project
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Equipment Data Sheet | L03-RE037-ME-DSH-002 23249-11
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 |  |  |  | Please refer to NOTE3 of datasheet | Updated as per P&ID. | NOTED
2 |  |  |  | MUST BE 300# | Updated. | NOTED
3 |  |  |  | Please implement this tag numbers to P&ID | Incorperated | NOTED
4 |  |  |  | Please implement this tag numbers to P&ID | Incorperated | NOTED
5 |  |  |  | Where is the oil cooler? | Oil cooler for compressor lubrication, integrated with the compressor. No separate data is available for the oil cooler, as it is manufactured standard. | NOTED
6 |  |  |  | Commented Please refer to page 3/6 PDF | Noted | NOTED
7 |  |  |  | ZONE 2, GAS GROUP IIC, TEMP. CLASS T3 Please consider and confirm | confirmed and updated in the datasheet | NOTED |  |  | Open
8 |  |  |  | Please add tag number like bellow items | this oil sump is inside the compressor block . This is noted in the next revision | NOTED |  |  | Closed
9
10
11
12
13
14
15
16
17
18
19
20